| General Objective | Specific Objectives | Actions | Immediate Steps | Timeframe | Responsible |  |
| --- | --- | --- | --- | --- | --- | --- |
| Recognize and address migration with a humanitarian approach, with the aim of ensuring protection of and differentiated assistance to boys, girls and adolescents. | Ensure the early identification of boys, girls and adolescents in vulnerable situations entering the country (foreign nationals as well as returned national citizens). | Establish efficient entry management systems (appropriate interviews, training and awareness-raising of officers on gender and age approaches). | Implement the use of a form including basic elements contained in the RCM Regional Guidelines for Identification and Referral. | Short term |  | Each country, with input from TS |
|  |  |  | Design and implement a training | Short term |  | Each country |
|  |  |  | A workshop on training of trainers provided by agents of the United States Child Protection System, to share their experience with officers from Member States of RCM providing assistance to migrant and refugee boys, girls and adolescents. | Short term |  | United States |
|  |  | Separate boys, girls and adolescents from the persons that accompany them, when appropriate. | Conduct a risk assessment. | Short term |  | System for the Protection of Boys, Girls and Adolescents Member States of RCM with support from international organizations for contents development TS, convene a meeting, El Salvador, Costa Rica and interested countries |
|  |  | Determine without delay if the boy, girl or adolescent is unaccompanied or separated. | Conduct a risk assessment. | Short term |  | System for the Protection of Boys, Girls and Adolescents Member States of RCM, with support from international organizations for contents development |
|  |  | Training and implementation of the Guidelines for the Identification and Referral of Migrants in Vulnerable Situations. | Ask IOM to organize the workshop. The target population will be officers from immigration and child protection institutions. The 3-day training will be conducted at a regional level: 1 day for training of trainers and 2 technical sessions. | Short term |  | IOM RCM - TS |
|  | Assess the best interest of the child and implement immediate assistance and protection actions (physical and psychosocial health, security, guardianship) considering the child’s opinion. | Coordination between government institutions, international organizations and civil society to ensure the appropriate implementation of immediate protection actions, including appropriate shelters. | Regional mapping of specialized shelters, including their management, through the establishment of alliances with churches, NGOs, universities or other actors | Short term |  | IOM |
|  |  | Designate a legal guardian (protection approach based on considering the boy, girl or adolescent as a subject with full rights). | Conduct a meeting to discuss principles, legal frameworks, procedures, statistics and best practices relating to assistance, protection and determination of the best interest of the boy, girl and adolescent. | Short term |  | Relevant institutions and Ministries of Foreign Affairs |
|  |  | Verify family ties and assess risks considering the best interest of the child. | A preliminary immediate assessment of the family resources, considering a risk assessment. | Short term |  |  |
|  |  |  | Review intra-institutional, inter-institutional and binational procedures in return processes and take the appropriate actions. | Short term |  |  |
|  |  | Verify relevant systems to search for missing boys, girls and adolescents, including the necessary coordination actions with involved States. | - Exchange information on search systems to develop a regional coordination mechanism. | Short term |  | Request support from the Red Cross |

| General Objective | Specific Objectives | Actions | Immediate Steps | Timeframe | Responsible |
| --- | --- | --- | --- | --- | --- |
| Recognize and address migration with a humanitarian approach, with the aim of ensuring protection of and differentiated assistance to boys, girls and adolescents. | Ensure the early identification of boys, girls and adolescents in vulnerable situations entering the country (foreign nationals as well as returned national citizens). | Establish efficient entry management systems (appropriate interviews, training and awareness-raising of officers on gender and age approaches). | Implement the Regional Guidelines of RCM and the mechanism for boys, girls and adolescents, incorporating mechanisms to review and assess implementation within the framework of a comprehensive assistance model. | Medium term | Child protection institutions, immigration authorities |
|  |  |  | - Implement the use of a form including basic elements contained in the RCM Regional Guidelines for Identification and Referral | Medium term | Each country, with input from TS |
|  |  |  | - Design and implement a training programme on awareness-raising for all officers providing assistance to boys, girls and adolescents, including experts and actors involved in the identification process, human rights ombudsman’s offices and civil society organizations (follow-up, visits to posts, etc.); the programme should be developed and implemented by each country or in a bilateral manner. | Medium term Ensure the sustainability-ty of the programme | Each country |
|  |  | Separate boys, girls and adolescents from the persons that accompany them, when appropriate. | Training on specific cases (case studies and analysis) to assess and determine the best interest of migrant and refugee boys, girls and adolescents | Medium term | System for the Protection of Boys, Girls and Adolescents Member States of RCM with support from international organizations for contents development TS, convene a meeting, El Salvador, Costa Rica and interested countries |
|  |  |  | Address this topic on the agenda of the Ad Hoc Group. El Salvador, Costa Rica and interested countries will share best practices. | Medium term |  |
|  |  | Determine without delay if the boy, girl or adolescent is unaccompanied or separated. | Develop a regional glossary of terms relating to migrant boys, girls and adolescents. | Medium term | System for the Protection of Boys, Girls and Adolescents Member States of RCM, with support from international organizations for contents development |
|  | Assess the best interest of the child and implement immediate assistance and protection actions (physical and psychosocial health, security, guardianship) considering the child’s opinion. | Coordination between government institutions, international organizations and civil society to ensure the appropriate implementation of immediate protection actions, including appropriate shelters. | Exchange experiences between Member States of RCM on specialized shelters. | Medium term | RCM |
|  |  |  | Create or strengthen inter-institutional committees for migrant boys, girls and adolescents; could be established by child protection institutions. | Medium term | Child protection institutions and immigration authorities |
|  |  |  | Develop a “Protocol for coordination among relevant government institutions to appropriately assist and protect returned boys, girls and adolescents” | Medium term | Governments of Member States of RCM |
|  |  | Respect the principle of non-refoulement of boys, girls and adolescents with potential needs for international protection, in accordance with national and international legislation. | Develop or strengthen procedures to assess and determine the best interest of the child. | Medium term | To be determined by each government |
|  |  |  | Training on international protection (with a main focus on child protection institutions). | Medium term and permanent Long term | International organizations |
|  |  |  | Designate a guardian or legal representative. | Medium term |  |
|  |  | Develop and implement pre-established protocols for referral to competent and appropriate protection institutions. | Adjust the guidelines approved by RCM to each national context. | Medium term |  |
|  |  | Designate a legal guardian (protection approach based on considering the boy, girl or adolescent as a subject with full rights). | Exchange experiences to determine which institution has legal representation of foreign boys, girls and adolescents in each country. | Medium term | Relevant institutions and Ministries of Foreign Affairs |
|  |  |  | Train institutions in charge of legal guardianship on human rights, with a focus on migrant and refugee boys, girls and adolescents. | Medium term |  |
|  |  | Verify family ties and assess risks considering the best interest of the child. | Promote binational coordination to ensure that consular notification is implemented at least 3 days in advance. | Medium term |  |
|  |  | Verify relevant systems to search for missing boys, girls and adolescents, including the necessary coordination actions with involved States. | Include the issue of missing boys, girls and adolescents in inter-institutional and regional coordination protocols. | Medium term |  |
|  |  | Assess the best interest of the boy, girl or adolescent to determine the actions that should be taken if a process to determine the best interest of the child (BIC) is not required. | Specific training on the BIC process. | Medium term | International organizations |
|  |  |  | Design an instrument of regional guidelines for action. | Medium term | International organizations |
|  | Establish an Operational Framework for Determining the Best Interest of the Child (BIC). | Take actions to provide foster care when required. | - Explore alternatives to institutionalization. | Medium term |  |
|  |  |  | - Exchange experiences on the systems that are in place in each country. | Medium term |  |

| General Objective | Specific Objectives | Actions | Immediate Steps | Timeframe | Responsible |
| --- | --- | --- | --- | --- | --- |
| Recognize and address migration with a humanitarian approach, with the aim of ensuring protection of and differentiated assistance to boys, girls and adolescents. | Ensure the early identification of boys, girls and adolescents in vulnerable situations entering the country (foreign nationals as well as returned national citizens). | Recording, verification of identity and nationality. | Identify basic information from the forms to share with the country of origin. | Long term |  |
|  |  |  | Promote an online system based on the comprehensive system for consular protection of Mexico. | Long term |  |
|  | Assess the best interest of the child and implement immediate assistance and protection actions (physical and psychosocial health, security, guardianship) considering the child’s opinion. | Coordination between government institutions, international organizations and civil society to ensure the appropriate implementation of immediate protection actions, including appropriate shelters. | Establish or strengthen specialized shelters for migrants. | Long term | RCM |
|  | Establish an Operational Framework for Determining the Best Interest of the Child (BIC). | Take actions to provide foster care when required. | Seek alternative family resources. | Long term |  |
|  |  |  | Establish a temporary mechanism for the protection of boys, girls and adolescents (in countries of return, transit and destination). | Long term |  |

| General Objective | Specific Objectives | Actions | Immediate Steps | Timeframe | Responsible |
| --- | --- | --- | --- | --- | --- |
| Recognize and address migration with a humanitarian approach, with the aim of ensuring protection of and differentiated assistance to boys, girls and adolescents. | Establish an Operational Framework for Determining the Best Interest of the Child (BIC). | Initiate actions to determine if the temporary separation of the boy, girl or adolescent from their parents against their will is the most convenient course of action, based on the best interest of the child, while waiting for a definitive judicial determination. | - Establish a temporary mechanism for the protection of boys, girls and adolescents (in countries of return, transit and destination). |  |  |
|  |  | Initiate actions to find the most appropriate lasting solution for refugee boys, girls and adolescents. | - Establish a temporary mechanism for the protection of boys, girls and adolescents (in countries of return, transit and destination). |  |  |

| General Objective | Specific Objectives | Actions | Immediate Steps | Timeframe | Responsible |
| --- | --- | --- | --- | --- | --- |
| Recognize and address migration with a humanitarian approach, with the aim of ensuring protection of and differentiated assistance to boys, girls and adolescents. | Ensure the early identification of boys, girls and adolescents in vulnerable situations entering the country (foreign nationals as well as returned national citizens). | Establish efficient entry management systems (appropriate interviews, training and awareness-raising of officers on gender and age approaches). | - Implement the Regional Guidelines of RCM and the mechanism for boys, girls and adolescents, incorporating mechanisms to review and assess implementation within the framework of a comprehensive assistance model. - Develop a protocol for psychosocial assistance upon reception that includes consular protection for boys, girls and adolescents, considering the existing guidelines developed by RCM. - Implement the use of a form including basic elements contained in the RCM Regional Guidelines for Identification and Referral. - Design and implement a training programme on awareness-raising for all officers providing assistance to boys, girls and adolescents, including experts and actors involved in the identification process, human rights ombudsman’s offices and civil society organizations (follow-up, visits to posts, etc.); the programme should be developed and implemented by each country or in a bilateral manner. - A workshop on training of trainers provided by agents of the United States Child Protection System, to share their experience with officers from Member States of RCM providing assistance to migrant and refugee boys, girls and adolescents. | Medium term Medium term Short term Medium term Ensure the sustainabili-ty of the programme Short term | Child protection institutions, immigration authorities IOM in coordination with countries Each country, with input from TS Each country United States |
|  |  | Recording, verification of identity and nationality. | - Identify basic information from the forms to share with the country of origin. - Promote an online system based on the comprehensive system for consular protection of Mexico. | Long term Long term |  |
|  |  | Separate boys, girls and adolescents from the persons that accompany them, when appropriate. | - Conduct a risk assessment. | Short term | System for the Protection of Boys, Girls and Adolescents Member States of RCM with support from international organizations for contents development TS, convene a meeting, El Salvador, Costa Rica and interested countries |
|  |  |  | - Training on specific cases (case studies and analysis) to assess and determine the best interest of migrant and refugee boys, girls and adolescents. - Address this topic on the agenda of the Ad Hoc Group. El Salvador, Costa Rica and interested countries will share best practices. | Medium term Medium term |  |
|  |  | Determine without delay if the boy, girl or adolescent is unaccompanied or separated. | - Conduct a risk assessment. | Short term | System for the Protection of Boys, Girls and Adolescents Member States of RCM, with support from international organizations for contents development |
|  |  |  | - Develop a regional glossary of terms relating to migrant boys, girls and adolescents. | Medium term |  |
|  |  | Training and implementation of the Guidelines for the Identification and Referral of Migrants in Vulnerable Situations. | - Ask IOM to organize the workshop. The target population will be officers from immigration and child protection institutions. The 3-day training will be conducted at a regional level: 1 day for training of trainers and 2 technical sessions. | Short term | IOM RCM - TS |
|  | Assess the best interest of the child and implement immediate assistance and protection actions (physical and psychosocial health, security, guardianship) considering the child’s opinion. | Coordination between government institutions, international organizations and civil society to ensure the appropriate implementation of immediate protection actions, including appropriate shelters. | - Regional mapping of specialized shelters, including their management, through the establishment of alliances with churches, NGOs, universities or other actors. | Short term | IOM |
|  |  |  | - Exchange experiences between Member States of RCM on specialized shelters. | Medium term | RCM |
|  |  |  | - Establish or strengthen specialized shelters for migrants. | Long term |  |
|  |  |  | - Create or strengthen inter-institutional committees for migrant boys, girls and adolescents; could be established by child protection institutions. | Medium term | Child protection institutions and immigration authorities |
|  |  |  | - Develop a “Protocol for coordination among relevant government institutions to appropriately assist and protect returned boys, girls and adolescents” | Medium term | Governments of Member States of RCM |
|  |  | Respect the principle of non-refoulement of boys, girls and adolescents with potential needs for international protection, in accordance with national and international legislation. | - Develop or strengthen procedures to assess and determine the best interest of the child. | Medium term | To be determined by each government |
|  |  |  | - Training on international protection (with a main focus on child protection institutions). | Medium term and permanent Long term | International organizations |
|  |  |  | - Designate a guardian or legal representative. | Medium term |  |
|  |  | Develop and implement pre-established protocols for referral to competent and appropriate protection institutions. | - Adjust the guidelines approved by RCM to each national context. | Medium term |  |
|  |  | Designate a legal guardian (protection approach based on considering the boy, girl or adolescent as a subject with full rights). | - Exchange experiences to determine which institution has legal representation of foreign boys, girls and adolescents in each country. | Medium term |  |
|  |  |  | - Conduct a meeting to discuss principles, legal frameworks, procedures, statistics and best practices relating to assistance, protection and determination of the best interest of the boy, girl and adolescent. | Short term | Relevant institutions and Ministries of Foreign Affairs |
|  |  |  | - Train institutions in charge of legal guardianship on human rights, with a focus on migrant and refugee boys, girls and adolescents. | Medium term |  |
|  |  | Verify family ties and assess risks considering the best interest of the child. | - A preliminary immediate assessment of the family resources, considering a risk assessment. | Short term |  |
|  |  |  | - Review intra-institutional, inter-institutional and binational procedures in return processes and take the appropriate actions. | Short term |  |
|  |  |  | - Promote binational coordination to ensure that consular notification is implemented at least 3 days in advance. | Medium term |  |
|  |  | Verify relevant systems to search for missing boys, girls and adolescents, including the necessary coordination actions with involved States. | - Include the issue of missing boys, girls and adolescents in inter-institutional and regional coordination protocols. - Exchange information on search systems to develop a regional coordination mechanism. | Medium term Short term | Request support from the Red Cross |
|  |  | Assess the best interest of the boy, girl or adolescent to determine the actions that should be taken if a process to determine the best interest of the child (BIC) is not required. | - Specific training on the BIC process. - Design an instrument of regional guidelines for action. | Medium term Medium term | International organizations International organizations |
|  | Establish an Operational Framework for Determining the Best Interest of the Child (BIC). | Take actions to provide foster care when required. | - Explore alternatives to institutionalization. | Medium term |  |
|  |  |  | - Seek alternative family resources. | Long term |  |
|  |  |  | - Establish a temporary mechanism for the protection of boys, girls and adolescents (in countries of return, transit and destination). | Long term |  |
|  |  |  | - Exchange experiences on the systems that are in place in each country. | Medium term |  |
|  |  | Initiate actions to determine if the temporary separation of the boy, girl or adolescent from their parents against their will is the most convenient course of action, based on the best interest of the child, while waiting for a definitive judicial determination. | - Establish a temporary mechanism for the protection of boys, girls and adolescents (in countries of return, transit and destination). |  |  |
|  |  | Initiate actions to find the most appropriate lasting solution for refugee boys, girls and adolescents. | - Establish a temporary mechanism for the protection of boys, girls and adolescents (in countries of return, transit and destination). |  |  |